## Sheet1
S.No | POA | Resposible | Expected date of completion | Reason | Actual date of completion
1 | Procedure for snapshot restoration in aws | IT Team
2 | Email Backup |  | Blocked | Waiting for approval from Martin
3 | EnableAMI Backups 1. OS Tickets 2. Snipe IT 3. ESSL 4. Zabbix | IT Team |  |  | 10th April
4 | Approved outbound Mailers list | IT Team |  |  | 12th April
5 | Exit Policy | HR | 10th april
6 | BGV | HR
7 | Induction program for Employees / Interns | HR | 10th april
8 | Multiple OFI's given in last audit | HR / IT Team |  | In progress
9 | Asset / Accessories tagging | IT Team |  | In progress
10 | Shredding policy | HR
11 | Policy Manual | IT Team |  | We work all policy in june month
12 | Security roles and responsibility - communicate with employee | HR
13 | Management approval on policy document | IT Team |  | We work all policy in june month
14 | Confidential - labelling | IT Team / HR
15 | Media handling | IT Team |  | We work all policy in june month
16 | Assets Registration - Responsibility | IT Team |  |  | 8th may
17 | Password Sharing policy | IT Team |  | We work all policy in june month
18 | Access Control | IT Team |  | We work all policy in june month
19 | Cryptography (Mail encryption) | IT Team | Blocked
20 | Protection against external and environmental threats cabling security | IT Team | Blocked | We already inform to Rathinam team and they did'nt responce
21 | Removal of assets - vendor indentified | IT Team
22 | Server room register | IT Team |  |  | 5th April
23 | Tailgating

## Sheet2
1. Previous Audit Report - 1st Minor NC - Action item to be clear. not only to take backup but to ensure the working condition of backed up data by IT team to be planned.
--Define steps for AWS snapshot restoration
2. Mgmt Approval for Backup required / not required - not available
--
1. Wazuh
-> AMI Backup:
-> Monthly 1 backup (3 months)
-> 7 days 1 back
-> Retention Period: 90 days
2. Os Ticket
-> AMI Backup:
-> Monthly 1 backup (3 Months)
-> 7 dats 1 backup
3. Snipe IT
-> AMI Backup:
-> Monthly 1 backup (3 Months)
-> 7 dats 1 backup
4. ESSL
-> AMI Backup:
-> Monthly 1 backup (3 Months)
-> 7 dats 1 backup
5. Zabbix
-> AMI Backup:
-> Monthly 1 backup (3 Months)
-> 7 dats 1 backup
6. GenAI
--> On App team's mail request.
7. Email Backup
--> Need to discuss with Martin and Suresh to confirm
--> Low Priority
3. Mgmt approval for Outbound Mailers list not available
IT team send the current list to get approval from CISO
Ideally, put timeframe for approval
4. exit policy - absconding - tighting up the policy - no evidance of action taken
Steps defined?
Close this by 10th Apr
5. Delay in BGV still there (getting initiated almost 15 days after employee onboarding)
day 2 need to initiate, need approval from CISO for exception witin5
more than 5 days, Mgmt should know why
6. Induction training for Employee / Intern - process / checklist not present
Inter/Consult: anyone coming to office should have a session
all consultants should send a checklist of do's and don't and get the ack
ETA : 10th Apr
7. There are multiple OFI's given in Last Audit on various aspects. It is good to have better plan to execute them.
8. Asset Accessories are not tagged yet - may needs attention
Get fixed
9. Shredding Machine is available - Shredding Policy shall be prepared
Define one policy
-Interview Resume withing
-Wrong offer letter
-Exit ID
Apr 10th
10. Policy Manual - Clause numbers are not matching with the document header numbers (good to have)
--Policy Manual docu to be changed: Pl reconfirm with Moosa once again
11. Security roles and responsibilities Roles and responsibilities defined? - to be communicated with employees
12. Management Approval on policy documents - shall be hand signed / email proof of approval
13. Confidentiality - labelling
14. Media Handling - process to be derived.
15. Asset Register - Receiver / Responsibility shall be maintained
16. Password Sharing policy to be derived
17. Access Control - policy to be detailed out
18. Cryptography - Mail - blocked
19. Protection against external and environmental threats & 11.2.3 Cabling security - blocked
20. 11.2.5 Removal of assets - Vendor shall be identified
21. Server Room Register - Shall maintain IN/OUT time
22. Tailgating - still seen